| # CAPACITY BUILDING ANNUAL WORKPLAN FOR MASINDI DISTRICT LOCAL GOVERNMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOR FINANACIAL YEAR 2021/2022 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| S/No. | Activity | Target No. | Target group | Location | Period |  |  |  |  | Budget |  | Responsible person |  | Source of funds |  |  |
|  |  |  |  | Sub county |  | Q1 | Q2 | Q3 | Q4 |  |  |  |  |  |  |  |  |
| 1 | Contribution to Staff in short term training Courses (Career Development) | 4 | District and sub-county staff | District/Sub-county |  |  |  |  |  |  | 8,000,000 |  | CAO PHRO | DDDEG |  |  |  |
| 2 | Capacity building needs assessment | 40 | All staff Masindi District | District wide |  |  |  |  |  |  | 1,500,000 |  | CAO PHRO | DDDEG |  |  |  |
| 3 | Orientation of Political Leaders on the new roles | 37 | District Councilors | District wide |  |  |  |  |  |  | 17,000,000 |  | CAO PHRO CLERK TO COUNCIL | DDDEG |  |  |  |
| 4 | Induction of new staff | 25 | Newly recruited and promoted officers | District wide |  |  |  |  |  |  | 3,000,000 |  | CAO PHRO | DDDEG |  |  |  |
| 5 | Sensitizing public officers on HIV/AIDs. | 20 | Heads of Department and Section | District wide |  |  |  |  |  |  | 2,000,000 |  | CAO PHRO HIV/AIDS FOCAL PERSON | DDDEG |  |  |  |
| 6 | Training of HOD/Section on succession planning | 20 | All HOD/Sections | District and Sub County |  |  |  |  |  |  | 2,500,000 |  | CAO CFO PHRO | DDDEG |  |  |  |
| 7 | Sensitizing staff in ethics and integrity | 25 | Masindi Hospital Departmental in charges and Lower Health units in charges | District |  |  |  |  |  |  | 2 ,000,000 |  | CAO PHRO | DDDEG |  |  |  |
| 8 | Sensitizing staff in Gender issues | 20 | Sub County Chiefs and CDO’s | Sub County |  |  |  |  |  |  | 2,000,000 |  | CAO PHRO DCDO | DDDEG |  |  |  |
| 9 | Performance Budget Based Systems | 22 | Heads of Department | District |  |  |  |  |  |  | 2,000,000 |  | CAO DISTRICT PLANNER | DDDEG |  |  |  |
| 10 | Training of staff in environmental management and conservation | 20 | Sub County Environment Focal Point Persons | Sub County |  |  |  |  |  |  | 2,500,000 |  | CAO DNRO HRO | DDDEG |  |  |  |
| 11 | Pre-retirement training | 25 | All staff due for retirement | District and Sub county |  |  |  |  |  |  | 2,500,000 |  | CAO SRO | DDDEG |  |  |  |
|  | Grand Total |  |  |  |  |  |  |  |  |  | 45,000,000 |  |  |  |  |  |  |

Compiled by

Opigo Cyrus

PRINCIPAL HUMAN RESOURCE OFFICER, MDLG